## Kanban Board
TO DO | IN PROGRESS | DONE
Important Dates
| T4: Build Model (ML) | T1: Source Datasets | 5th October | Initial proposal due
| Description: Program the | Description: Collects Datasets | 19th October | Technical Proposal
| machine learning model | from sites such as Kaggle | 24th October | Project Presentation
|  |  | 14th November | Techincal review and Design document due
|  |  | 12th December | Codeing week
| Due Date: 13/11/ 22 | Due Date: 16/10/22 | 16th January | Demo project Prototype
| Estimated Time: 2 Weeks | Estimated Time: 1 week | 17th January | Individual asessment
| Asignee: Patryk and Daniel | Asignee: Patryk | 10th February | Upload all Code
|  |  | 10th February | E-copy of all documentation to be uploaded
| T5: Train the model (ML) | T2: Data preprocessing | 14th February | Demo and Present project
| Description: Feeding the | Description: cleaning the data
| training data into the model | format it
and predicting results
| Due Date: 27/11/22 | Due Date: 30/10/22
| Estimated Time: 2 weeks | Estimated Time: 2 weeks
| Asignee: Ingrid | Asignee: Ingrid
T6: Improve Model Accuracy
Description: Making any
changes to our model in
order to maximise accuracy
Due Date: 11/12/22
Estimated Time: 2 weeks
Asignee: All
Task : Develope HTML Code
Description: Build the HTML
of the front end
Due Date: 18/12/22
Estimated Time: 1 week
Asignee: Daniel
Task : Develop JavaScript
Description: Provide good
functionality to the front end
Due Date: 18/12/22
Estimated Time: 1 Week
Asignee: Patryk
Task : Style Front-End (CSS)
Description: Style the HTML
Code for the front end
Due Date: 18/12/22
Estimated Time: 1 Week
Asignee: Ingrid

## Gantt Chart
Task | Start Date | End Date | Duration
Source dataset | 2022-10-10 | 2022-10-16 | 6
data Preprocessing | 2022-10-17 | 2022-10-30 | 13
Build machine learning model | 2022-10-31 | 2022-11-13 | 13
Train the machine learning model | 2022-11-14 | 2022-11-27 | 13
Improve model Accuracy | 2022-11-28 | 2022-12-11 | 13
Develop HTML code | 2022-12-12 | 2022-12-18 | 6
Develop JavaScript code | 2022-12-12 | 2022-12-18 | 6
Style Front-End (CSS) | 2022-12-12 | 2022-12-18 | 6

## Kanban Cards
Datasets | T1: Source Datasets | T2: Data preprocessing
Description: | Description: Collects Datasets | Description: cleaning the data |  | T4: Build Model (ML)
| from sites such as Kaggle | format it |  | Description:
Due Date: | Due Date: 16/10/22 | Due Date: 30/10/22
Estimated Time: | Estimated Time: 1 week | Estimated Time: 2 weeks |  | Due Date:
Asignee: | Asignee: Patryk | Asignee: Ingrid |  | Estimated Time:
Asignee:
Machine learning | T4: Build Model (ML) | T5: Train the model (ML) | T6: Improve Model Accuracy
Description: | Description: Program the | Description: Feeding the | Description: Making any
| machine learning model | training data into the model | changes to our model in
|  | and predicting results | order to maximise accuracy
Due date: | Due Date: 13/11/ 22 | Due Date: 27/11/22 | Due Date: 11/12/22
Estimated Time: | Estimated Time: 2 Weeks | Estimated Time: 2 weeks | Estimated Time: 2 weeks
Asignee: | Asignee: Patryk and Daniel | Asignee: Ingrid | Asignee: All
Front-End | Task : Develope HTML Code | Task : Develop JavaScript | Task : Style Front-End (CSS)
Description: | Description: Build the HTML | Description: Provide good | Description: Style the HTML |  |  |  |  | T 3: Create Training Database
| of the front end | functionality to the front end | Code for the front end |  |  |  |  | Description:
Due Date: | Due Date: 18/12/22 | Due Date: 18/12/22 | Due Date: 18/12/22
Estimated Time: | Estimated Time: 1 week | Estimated Time: 1 Week | Estimated Time: 1 Week |  |  |  |  | Due Date:
Asignee: | Asignee: Daniel | Asignee: Patryk | Asignee: Ingrid |  |  |  |  | Estimated Time:
Asignee:
after Ds and ML - split into 2 parts Group1 look at honeypot, group 2 - put pieces together for rest of project
create honey-pot log DB
[5 empty] | Description |  |  |  | Description
[5 empty] | Due Date: |  |  |  | Due Date:
[5 empty] | Estimated Time: |  |  |  | Estimated Time:
[5 empty] | Assignee |  |  |  | Assignee
feed Honey-pot log data into ML model
Description
Due Date:
Estimated Time:
Assignee
Honey-pot
Description
Due Date:
Estimated Time:
Assignee